## 5-Year Roadmap
|  | Lead | Timeline | Additional Resources Needed? | D | E | I | A | Notes
Goal 1: Leadership & Operations
Objective 1.1: Foster community engagement and inclusivity in decision-making.
1.1.1 | City Council members to continue to meet with the community to discuss important local issues. | City Council | ongoing | No |  |  | ✓
1.1.2 | City Manager will maintain an informal DEIA Advisory Committee to advise the city manager and staff on policy and operational issues. Create and maintain a charter for this committee. | City Manager's Office | ongoing | No | ✓ | ✓ | ✓ | ✓
1.1.3 | When engaging the community in planning and decision making, make extra and affirmative efforts to bring in members of the community who have not historically participated. Provide less traditional and more inclusive and accessible opportunities for public input and engagement, such as hands-on engagement models and “pop up” engagement opportunities in neighborhoods. | City Manger's Office | 2023 | Yes | ✓ |  | ✓ |  | Will need to budget ongoing funding for this extra effort in the next biennium
1.1.4 | Coffee with Council – continue to provide alternating accessible options to attend. | City Council | ongoing | No |  |  | ✓
1.1.5 | Refer to the equity toolkit in policymaking. Distribute the toolkit to City Council, Planning Commission, and all staff and provide training on the toolkit. | City Council & All Departments | 2023 | No |  | ✓ | ✓
Objective 1.2: Ensure equitable access and representation in city services.
1.2.1 | Identify and retain important public access and view corridors to Lake Washington and the Sammamish River for all of the public to enjoy. | Community Development | 2024 | Yes |  | ✓ |  | ✓ | Part of next Comp Plan Update
1.2.2 | Maintain and update the Parks, Recreation and Open Space (PROS) plan using the equity toolkit. Plan for more parks and amenities in underserved parts of the City and for people of all abilities. | Community Development | 2026 | Some consulting dollars will be needed |  | ✓ |  | ✓
1.2.3 | Accept applications in the order received, with exceptions for affordable housing projects, public city projects aimed at increasing public access to services and amenities, and applications that support implementation of the Climate Action Plan, all of which shall be fast-tracked for rapid processing. | Development Services | ongoing | No |  | ✓
1.2.4 | Provide increased access to permit submittals by continuing to accept applications online. In-person paper submittals also accepted as an accommodation upon request. | Development Services | ongoing | No |  |  |  | ✓
Objective 1.3 Facilitate ways to increase diverse representation among City vendors and Committee and Commission members.
1.3.1 | Requests for Proposals (RFPs), bid advertisements, and all other purchasing and procurement materials will include language about the city's equity and social justice values. When issuing a request for proposals or other solicitation for services, specifically reach out to and invite women and minority owned businesses to submit quotes and proposals. | All Departments | 2023 | No | ✓ | ✓ | ✓
1.3.2 | When issuing RFPs and other solicitations for services, consider barriers for first-time proposers; provide guidance on and be available to assist with the technical aspects of the solicitation that might be new territory for people who are trying to make entry and gain a foothold in serving cities. | All Departments | 2023 | No | ✓ | ✓ | ✓ | ✓
1.3.3 | Create and maintain a City of Kenmore Supplier Diversity Program for procurement; set appropriate goals for participation of minority, women, and socially and economically disadvantaged businesses. | Finance & Administration | 2025 | Yes | ✓ |  | ✓
1.3.4 | Utilize the services of the state Office of Minority and Women's Business Enterprises (OMWBE) to encourage and assist women- and minority-owned businesses in competing for contracts and doing business in the City. | City Manager's Office | 2024 | No | ✓ |  | ✓
1.3.5 | Planning Commission and other committee selection criteria should support broad demographic representation. | Community Development | 2023 | No | ✓
Objective 1.4: Support businesses and projects that align with equity goals.
1.4.1 | Expedite plan review for affordable housing projects and public city projects that increase public access to services and amenities. | Development Services | 2024 | No |  | ✓
1.4.2 | Continue the City’s membership in A Regional Coalition for Housing (ARCH), including leveraging ARCH’s resources to build affordable housing units in Kenmore and contributing financial resources to ARCH’s housing trust fund. | Development Services & City Manager's Office | ongoing | No |  | ✓
1.4.3 | Support businesses in their permit process by providing efficient and predictable services; identify and address barriers or challenges for businesses that may be new to the City's processes. | Development Services | ongoing | No |  | ✓ |  | ✓
Objective 1.5: Strengthen leadership commitment to diversity, equity, inclusion, and accessibility.
1.5.1 | Communicate both the significance and value-add of DEIA openly; broadening this circle of communication to include staff, community, and leadership. | City Manager's Office | ongoing | No | ✓ | ✓ | ✓ | ✓
1.5.2 | Create and maintain a respectful, inclusive, and professional working environment that promotes safety (including psychological safety) and inclusion, and that values difference. | Development Services | ongoing | No |  |  | ✓
1.5.3 | Ensure leaders are accountable for DEIA objectives, collaboration, and key results. | All Departments | ongoing | No | ✓ | ✓ | ✓ | ✓
1.5.4 | Implement this 5-Year Strategic DEIA Plan and integrate it into the organization. | All Departments | 2023-2028 | Yes | ✓ | ✓ | ✓ | ✓
Objective 1.6: Ensure accountability through data collection and performance measures.
1.6.1 | Collect demographic and geographic (GIS) information to analyze potential differences between communities and to assist the City in its efforts to have vendors and Committee and Commission recruitments reflect the community. Seek ways to identify languages spoken in the Kenmore community. | Community Development | ongoing | No | ✓ | ✓ | ✓
1.6.2 | Update the Strategic DEIA Action Plan every five years to align with the goals of the City of Kenmore. | City Manager's Office | 2028 | Yes | ✓ | ✓ | ✓ | ✓
1.6.3 | Develop a set of performance measures to assess progress toward realization of this DEIA Strategic Plan. Include these measures in periodic reporting. | All Departments | 2023 | No | ✓ | ✓ | ✓ | ✓
1.6.4 | Conduct a bi-annual City of Kenmore Employee Survey. | Human Resources | 2024, 2026, 2028 | No | ✓ | ✓ | ✓ | ✓
1.6.5 | Conduct a City of Kenmore Community Survey every 3 years. | City Manager's Office | 2023, 2026 | Yes | ✓ | ✓ | ✓ | ✓
1.6.6 | Participate in the Human Rights Campaign Municipal Equality Index. | City Manager's Office | 2024 | TBD | ✓ | ✓ | ✓
Objective 1.7: Strengthen the Organization's Working Knowledge, Integration, and Practice of DEIA.
1.7.1 | Ensure that staff resources are allocated to the implementation of this City of Kenmore DEIA strategic initiative. | All Departments | 2023-2028 | Yes | ✓ | ✓ | ✓ | ✓
1.7.2 | Participate in mandatory, DEIA training and/or learning events every two years. (A list of training and learning opportunities shall be maintained by Human Resources). | Human Resources | 2024, 2026, 2028 | Yes | ✓ | ✓ | ✓ | ✓
1.7.3 | Include DEIA training at new employee orientation. The new employee orientation packet should include the DEIA Policy, this Strategic Plan, and the equity toolkit, among other DEIA resources. | Human Resources | 2024 | No | ✓ | ✓ | ✓ | ✓
1.7.4 | Track City Council Member DEIA training and learning participation and make reporting available for public information through the City Clerk’s office. | City Clerk | 2023-2028 | No | ✓ | ✓ | ✓ | ✓
Goal 2: Plans, Policies & Budgets
Objective 2.1: Develop and implement inclusive and equitable policies.
2.1.1 | The Comprehensive Plan and other city-wide planning documents and regulations will be developed and written with a focus on DEIA and will include policies in its elements that advance DEIA and root out systemic inequity. | All Departments | 2023-2028 | No | ✓ | ✓ | ✓ | ✓
2.1.2 | All City policies, procedures, and manuals are written and reviewed with a focus on DEIA. These documents will include references to DEIA and the importance thereof. | All Departments | 2023 | No | ✓ | ✓ | ✓ | ✓
2.1.3 | City Manager will consult with the DEIA Advisory Committee as needed on potential policy and operation issues that may arise. | City Manager's Office | ongoing | No | ✓ | ✓ | ✓ | ✓
Objective 2.2: Engage the community in budget and policy decision-making.
2.2.1 | Host listening sessions with the public regarding remaining American Rescue Plan Act (ARPA) funds that are yet to be allocated. | City Manager's Office | 2023 | No |  |  | ✓
2.2.2 | Use online and in person community engagement tools to gather public input. | City Manager's Office | 2023 | Yes | ✓ |  | ✓ | ✓
2.2.3 | Think outside of the box to bring more people of diverse backgrounds into policy discussions. Make extra and affirmative efforts to bring in members of the community who have not historically participated. | All Departments | 2023 | Yes | ✓ |  | ✓ | ✓ | Staffing resources needed to make the extra outreach.
2.2.4 | Publish the budget online and in hard copy in several locations. | Finance/Administration | 2023 | No |  |  |  | ✓
2.2.5 | Provide a budget development process that is transparent and open to the public. | Finance/Administration | 2024, 2026, 2028 | No |  |  | ✓
Objective 2.3: Develop and advocate for affordable housing and diverse housing options.
2.3.1 | Expedite plan review for affordable housing projects and public city projects that increase public access to services and amenities. | Development Services | 2023 | No |  | ✓ |  | ✓
2.3.2 | Develop and adopt planning and zoning regulations that will prioritize affordable and more attainable housing. | Community Development | ongoing | No | ✓ | ✓
2.3.3 | Develop land use regulations that allow for a diversity of housing types and choices for different needs. | Community Development | underway | No | ✓ | ✓ |  |  | Implementing regulations expected to come forward in 2024
2.3.4 | Implement the Transit Oriented Development (TOD) regulations that mandate higher densities and affordable units in the TOD area. (TOD requires 25% of units to be affordable at 50% of area median income or lower.) | Community Development | 2023 | No |  | ✓ |  |  | Adopted in March 2023
2.3.5 | Implement the residential tenant protection measures adopted by the City Council. | Community Development | underway | No |  | ✓ |  |  | Adopted in 2022
2.3.6 | Advocate for additional affordable housing policies at federal, state, and county levels. | Community Development | underway | Yes |  | ✓
Objective 2.4: Promote economic development opportunities that benefit all Kenmore residents and businesses.
2.4.1 | Dig deeper into the experiences and outcomes of underrepresented groups in the business community and city-wide workforce. Based on what is learned, recommend policies and operational changes to lift and support these groups. | City Manager's Office | 2025 | Yes | ✓ | ✓ | ✓
2.4.2 | Increase efforts to build partnerships that support and retain local businesses and organizations, with an emphasis on supporting underrepresented and marginalized groups in the business community. | City Manager's Office | 2023/2024 | Yes | ✓ |  | ✓ |  | Will need to expand functionality of the business directory.
2.4.3 | Collect data and feedback from business community members, the Chamber of Commerce, workers, and other relevant stakeholders to best understand the needs and experiences of business owners and workers who are impacted by the policies, processes, and programs executed by the City of Kenmore. | City Manager's Office | 2025 | Yes | ✓ |  | ✓
2.4.4 | Continue partnership with Bothell Kenmore Chamber of Commerce and the Kenmore Business Alliance to support local businesses. | City Manager's Office | ongoing | No |  |  | ✓
2.4.5 | Encourage participation of women- and minority-owned businesses in Kenmore Business Alliance activities. | City Manager's Office | ongoing | No | ✓ |  | ✓
2.4.6 | Advocate for a broader diversity of business types through external networks and the OMWBE. | City Manager's Office | 2024-2028 | No | ✓ |  | ✓
2.4.7 | Support and promote green jobs and companies given their connection to environmental equity and social justice. | City Manager's Office | 2024 | Yes |  | ✓
Objective 2.5: Adopt policies and practices that prioritize equity, accessibility, and inclusivity.
2.5.1 | Adopt a Non-Discrimination Ordinance. | City Council | 2024 | No | ✓ |  | ✓
2.5.2 | Honor the name, gender designation, and pronoun/non-pronoun of each employee and community member and encourage staff and community members to respect them. | All Departments | ongoing | No |  |  | ✓
Objective 2.6: Enhance recreational and cultural opportunities to improve DEIA in Kenmore.
2.6.1 | Support organizations that offer recreation, arts, and cultural programs and events. | Public Works Operations & City Manager's Office | ongoing | No | ✓ |  | ✓ | ✓
2.6.2 | Commission art projects with the 1% for Arts fund. Specifically reach out to BIPOC artists and invite them to submit proposals for art. | Public Works Operations & City Manager's Office | ongoing | No | ✓ |  | ✓
2.6.3 | Seek additional partnerships for recreation programming at existing parks and facilities. | Public Works Operations | ongoing | Yes |  | ✓ | ✓ |  | May need additional funding for low-income participants
2.6.4 | Partner with waterfront programming providers (Kenmore Waterfront Activites Center, Northshore School District, rowing, etc.) for affordable access to non-traditional rowers. Continue to require KWAC and rowing programs to provide low income scholarships. | Public Works Operations | ongoing | No |  | ✓ | ✓
2.6.5 | Continue to seek external funding to provide public access and recreation opportunities, especially for low income youth. | Public Works Operations | ongoing | Yes | ✓ | ✓ | ✓ | ✓
2.6.6 | Continue to partner with the nonprofit and for-profit organizations to provide recreational and development opportunities for youth (e.g., Skyhawks at Rhododendron Park and Skate Like a Girl at the Jack Crawford Skate Court). | Public Works Operations | ongoing | No |  | ✓ | ✓ | ✓
2.6.7 | Collaborate with Kenmore Heritage Society to create awareness, including providing learning and education opportunities, of Local Indigenous People. | City Manager's Office | ongoing | No | ✓ |  | ✓
2.6.8 | Consider subsidizing swimming lessons for low income youth. | Public Works Operations | 2023-2024 | Yes |  | ✓ |  |  | Funding needs to be identified beyond 2023. Currently being funded with one-time reserves.
2.6.9 | Offer free, inclusive events, special events, outdoor movies, and concerts for the community. | Public Works Operations | ongoing | No |  |  | ✓ | ✓
2.6.10 | Diversify event schedules, explore new promotion avenues, and support external community events. | Public Works Operations | ongoing | Yes | ✓ |  | ✓ | ✓ | Additional staffing resources may be needed for additonal external events
2.6.11 | Partner with nonprofits and other agencies to host community events and presentations focused on low-income populations. | City Manager's Office | 2025 | Yes |  | ✓
2.6.12 | Lead an effort to create a regional partnership to build a regional aquatic center in north King County. | Community Development | 2023-2028 | Yes |  | ✓ |  | ✓ | Feasibility study currently underway
2.6.13 | Work cooperatively with Bastyr University for use of their campus athletic fields. Look to partner with Bastyr University in other potential ways, such as youth summer camps. | Public Works Operations | ongoing | No |  | ✓ |  | ✓
Goal 3: Workplace
Objective 3.1: Create and maintain an inclusive workplace culture.
3.1.1 | Promote and follow the organization service vision as well as the core and foundational values. | City Manager's Office | ongoing | No | ✓ | ✓ | ✓ | ✓
3.1.2 | Increase awareness and working knowledge of the City’s Anti-Harassment Policy and other personnel policies pertaining to equity and justice in the workplace. | Human Resources | 2023, 2025, 2027 | No |  | ✓ |  |  | Regular training schedule
3.1.3 | Continue to provide Parental Leave for all employees. Upon returning from parental leave, supervisors will check in with the employee and discuss any supportive accommodations that employees may require, such as any physical limitations, pump breaks, flex scheduling for appointments, etc. | Finance/Administration | ongoing | No |  | ✓
3.1.4 | Regularly highlight and review the City Council-adopted DEIA Policy. | City Manager's Office | ongoing | No | ✓ | ✓ | ✓ | ✓
3.1.5 | Encourage cross-departmental relationships and communication through internal committees. | All Departments | ongoing | No | ✓ |  | ✓
3.1.6 | Model the behaviors that are expected of all staff to be equitable, inclusive, and create a culture of belonging. | All Departments | ongoing | No | ✓ | ✓ | ✓
3.1.7 | Provide clear and accessible channels for City staff to provide feedback on the workplace environment and job satisfaction. | Human Resources | 2023 | No | ✓ | ✓ | ✓
Objective 3.2: Develop and implement equitable hiring practices.
3.2.1 | Strive for diverse hiring panels during the interview process. | Human Resources | ongoing | No | ✓
3.2.2 | Ensure that hiring panelists have had DEIA training, including implicit bias training, prior to participating on the panel. | Human Resources | ongoing | No | ✓ | ✓ | ✓ | ✓
3.2.3 | Ask DEIA questions of candidates during interviews. | Human Resources | ongoing | No | ✓ | ✓ | ✓ | ✓
3.2.4 | Advertise positions through diverse outlets. | Human Resources | ongoing | No | ✓ |  | ✓
3.2.5 | Establish consistent hiring practices for reaching diverse populations; reach out to and invite minorities and members of historically marginalized groups to apply for open positions. | Human Resources | ongoing | No | ✓ |  | ✓
3.2.6 | Explore a work study program. | Human Resources | 2024 | Yes |  | ✓
3.2.7 | Research equitable hiring practices in neighboring cities. | Human Resources | 2024 | No |  | ✓
Objective 3.3: Provide professional development and advancement opportunities.
3.3.1 | Encourage employees to participate in their professional organizations. | All Departments | ongoing | No |  | ✓
3.3.2 | Continue the tuition reimbursement program. | Human Resources | ongoing | No |  | ✓
3.3.3 | Support career advancement through leadership training such as the Northwest Women's Leadership Academy. | All Departments | ongoing | No | ✓ | ✓
3.3.4 | Make consistent and planned efforts to grow and promote internal staff. Track promotion history to assess progress. (Succession Planning) | Human Resources | ongoing | No | ✓ | ✓
Objective 3.4: Offer competitive employee benefits and support systems.
3.4.1 | Continue to provide competitive benefits to city employees (Healthcare, EAP, retirement, etc.). | Human Resources | ongoing | No |  | ✓ |  | ✓
3.4.2 | Continue monthly all-staff meetings that are inclusive and highlight DEIA. | City Manager's Office | ongoing | No | ✓ | ✓ | ✓ | ✓
3.4.3 | Continue to fund and implement the City’s Wellness Program (e.g., floating holiday for healthy practices). | Human Resources | ongoing | No |  | ✓
3.4.4 | Continue the length of service awards program, including the event that goes with it (see Section 5.5 of the Personnel Policies Manual). | Human Resources | ongoing | No |  | ✓
3.4.5 | Continue to allow for brief and informal gatherings to celebrate birthdays and other personal milestones (see Section 5.6.5 of the Personnel Policies Manual). | All Departments | ongoing | No |  |  | ✓
3.4.6 | Adopt a Commute Trip Reduction Plan that promotes non-car commute options and resources. | City Manager's Office | 2025 | Yes |  | ✓ |  | ✓
3.4.7 | Support KCSO Officer wellness and resiliency programs. | City Manager's Office | ongoing | No |  | ✓
Objective 3.5: Monitor and assess workplace and workforce diversity.
3.5.1 | Research how to and begin collecting voluntary demographic data from applicants and new hires so that the City can assess whether the workplace is reflecting the greater community. | Human Resources | 2024 | Yes | ✓ |  | ✓
Goal 4: Communication & Education
Objective 4.1: Improve accessibility and inclusivity of communications across all channels.
4.1.1 | Continue to utilize electronic channels: City of Kenmore Website, website calendar, Social Media (Facebook, Twitter, Instagram), Monthly E-news, Weekly Kenmore Top 4, Email listservs for city meetings/events, projects and other specific topics. | City Manager's Office | ongoing | No |  |  | ✓
4.1.2 | Continue to implement paper-based communication methods: Kenmore Quarterly Newsletter, Postcard mailings, SEPA & Advisory Mailings, Postings at City Hall/the Hangar. | City Manager's Office | ongoing | No |  | ✓ | ✓ | ✓
4.1.3 | Ensure City of Kenmore digital and printed materials use accessible fonts and colors, approved by Web Content Accessibility Guidelines (WCAG) 2.0. Use Bureau of Internet Accessibility online tool to check for color blindness accessibility when using color in materials. Use approved accessible fonts when possible (Roboto, Tahoma, Verdana, Open Sans, Calibri, and Times New Roman are the top choices). | City Manager's Office | 2023 | No |  |  |  | ✓
4.1.4 | Offer translated communications in Spanish and other community languages on the website, listserv emails, and printed materials and publicize availability of translation services by phone. | City Manager's Office | ongoing | Yes |  |  | ✓ | ✓ | Spanish currently provided; need additonal resources for other languages
4.1.5 | Utilize the Userway tool on the website for enhanced translation and accessibility tools. | City Manager's Office | ongoing | No |  |  | ✓ | ✓
4.1.6 | Expand the use of QR codes on notices, mailings, and digital materials to provide easy access to information in multiple languages. | City Manager's Office | 2023 | No |  |  | ✓ | ✓
4.1.7 | Create video tutorials for online permit applications. Provide Spanish subtitles and closed captioning. | Development Services | 2024 | No |  |  | ✓ | ✓
4.1.8 | Maintain a public page on the City of Kenmore website with updates, information, and resources for the Kenmore community to understand, be made aware of, and participate in the City of Kenmore’s DEIA strategies, goals, and results. | City Manager's Office | ongoing | No | ✓ | ✓ | ✓ | ✓
4.1.9 | Create a fun and engaging Civics 101 video course to help residents better understand the workings of city government. Provide Spanish subtitles. | City Manager's Office | ongoing | Yes |  |  |  | ✓ | Difficult/slow to implement with existing resources
4.1.10 | Develop and maintain a list of individuals and agencies who can provide translation services for public meetings and other needs as they arise. | City Manager's Office | 2023 | No | ✓ |  | ✓ | ✓
4.1.11 | Make efforts to ensure accessibility for hearing-impaired individuals at city-sponsored and supported events. | City Manager's Office | 2024 | No |  | ✓ |  | ✓
Objective 4.2: Enhance community engagement through targeted messaging and recognition of diverse cultures and histories.
4.2.1 | Implement an annual Proclamations Calendar to recognize and celebrate diverse communities and their histories. | City Clerk | ongoing | No | ✓ |  | ✓
4.2.2 | Install parks interpretive signage to educate about environmental sustainability and community history. | Community Development | 2026 | Yes | ✓ |  |  |  | Completed parks projects have this signage.
4.2.3 | Annually produce a Juneteenth event to commemorate the liberation of Black Americans from slavery. Include the affected groups in the planning and execution of these events. | Public Works Operations | ongoing | No | ✓ |  | ✓
4.2.4 | Continue June Pride Month activities, including the annual Pride flag raising. Include the affected groups in the planning and execution of these events. | Public Works Operations | ongoing | No | ✓ |  | ✓ |  | In a facilitation role on events led by the community
4.2.5 | Provide for avenues to celebrate diversity at City events. | Public Works Operations | ongoing | No | ✓ |  | ✓
4.2.6 | Invite cultural groups to host events in Kenmore, e.g., the Festival of Colors in the Spring. | Public Works Operations | 2024 | Yes | ✓ |  | ✓
Goal 5: Facility Plans & Improvements
Objective 5.1: Enhance the safety, accessibility, and inclusivity of parks and city-owned buildings.
5.1.1 | Evaluate and ensure parks, buildings, and other public facilities are safe, well-maintained, and operate efficiently. | Public Works Operations | ongoing | No |  |  |  | ✓
5.1.2 | Improve access to parks and playgrounds. Seek guidance from inclusive experts such as The Voice of Play. | Community Development | 2028 | Yes |  |  | ✓ | ✓
5.1.3 | Change City restroom signage to be more inclusive of gender identities. | Community Development | 2024 | No |  |  | ✓
5.1.4 | Continue to supply and maintain life jacket loaner stations at waterfront parks. | Community Development | ongoing | No |  | ✓ |  | ✓
Objective 5.2: Improve transportation safety and accessibility for multiple modes of transportation so that owning an automobile isn’t the only way to get around.
5.2.1 | Develop parks and transportation plans that improve public access and mobility as well as recreational opportunities. | Community Development & Engineering Services | 2024 and 2026 | Yes |  |  |  | ✓ | 2024 for Transportation Plan and 2026 for the PROS Plan
5.2.2 | Obtain funding for and implement the first phase of the ADA transition plan, including replacing noncompliant sidewalk panels and curb ramps. Develop the next phase of the ADA transition plan to include City buildings. | Public Works Engineering | 2023-2028 | Yes |  |  | ✓ | ✓
5.2.3 | Implement and obtain funding for the adopted pedestrian facilities plan. | Public Works Engineering | 2023-2028 | Yes |  |  |  | ✓
5.2.4 | Continue to calm vehicle traffic to improve bicycle and pedestrian safety and comfort. | Public Works Engineering | 2023-2028 | Yes |  |  |  | ✓
5.2.5 | Advocate for completion of the Sound Transit Bus Rapid Transit project through Kenmore and advocate for additional bus routes and “last mile” transit options for Kenmore. | Public Works Engineering | 2023-2028 | Yes |  | ✓ |  | ✓
5.2.6 | Explore options and funding to provide more bike racks in public and private locations throughout the City. | Public Works Engineering | 2024 | Yes |  | ✓ |  | ✓
5.2.7 | Promote King County’s Community Van, Metro Flex, and other accessible transportation programs. | City Manager's Office | ongoing | No |  | ✓ |  | ✓
Objective 5.3: Update facility plans to reflect community needs and promote equity.
5.3.1 | Ensure capital facilities plans recognize and provide projects and programs in underserved areas. | Community Development | 2026 | Yes |  | ✓
5.3.2 | Consider community vulnerabilities related to climate and proactively respond (e.g., cooling center for impacted community members). | Environmental Services | 2024 | Yes |  | ✓
5.3.3 | Equitably provide green energy infrastructure in higher density and lower income neighborhoods. | Environmental Services | 2025 | Yes |  | ✓
5.3.4 | Reduce the heat-island effect that disproportionately affects disadvantaged neighborhoods by developing a plan to encourage and provide more trees and natural landscape to those areas. | Environmental Services | 2025 | Yes |  | ✓
5.3.5 | Equitably replace assets before reaching the end of their expected life cycle; use a fair, systematic approach to asset replacement and repair rather than the “squeaky wheel” approach. | Public Works Operations | 2025 | Yes |  | ✓
Goal 6: Public Safety & Justice Services
Objective 6.1 Advance the police department’s progress in equitably serving and responding to the community.
6.1.1 | Chief of Police to annually hold listening sessions with the community. | Police | 2024 | No |  | ✓ | ✓
6.1.2 | Continue to implement the preventative and healing measures identified in the 2020 Mayor’s Pledge Use of Force Report. | Police | ongoing | No |  | ✓
6.1.3 | Continue to augment police training, including prevention-oriented training such as cultural diversity, de-escalation, and active bystander training. Offer human services-related training to police officers, including crisis intervention and interacting with persons with disabilities through the Criminal Justice Training Commission and KCSO Advanced Training Unit. | Police | ongoing | No | ✓ | ✓ | ✓
6.1.4 | Explore and advocate for prevention-oriented methods to reduce patrol stops that disproportionately affect people of color. For example, explore the use of technology as a replacement for traffic stops and as a way to reduce the potential for violent encounters. | Police | 2025 | Yes |  | ✓
6.1.5 | Identify low-level offenses (e.g. DWLS3) that can cause disadvantaged populations to get stuck in a vortex of economic disparity and impoverishment. Take a holistic, preventative, and healing approach to work with the prosecutor, public defender, court, and human services providers to help people out of this vortex. | Police and Justice Services | ongoing | Yes |  | ✓
6.1.6 | Work closely with the Regional Crisis Response (RCR) program to co-respond with mental health professionals. | Police | ongoing | No |  | ✓ |  | ✓
6.1.7 | Become knowledgeable of various human services providers that can assist with cases. Refer individuals to these organizations. Refer individuals to the resource center at the community court. Participate in the community court stakeholder meetings and recommend offenders to the community court when appropriate. | Police | ongoing | No |  | ✓ | ✓ | ✓
6.1.8 | Connect and frequently communicate with the City’s Housing and Human Services Manager to coordinate ways to prevent human suffering and help lift people out of the cycle of the criminal justice system, reducing recidivism and future crimes. | Police | 2023-2028 | No |  | ✓ | ✓ | ✓
6.1.9 | Participate in the King County Sheriff Department’s body worn cameras program. | Police | 2023, 2024 | Yes |  | ✓ |  |  | Body worn cameras result in added cost to the police contract.
6.1.10 | Bring back the Nurturing Trust Workshops that build trust between police and communities of color. | Police | 2025 | Yes | ✓ | ✓ | ✓
6.1.11 | Research the potential effectiveness and resources needed to produce an academy for residents to learn about police and justice services. Specifically invite people of color and marginalized groups. | Police | 2025 | Yes |  | ✓ | ✓
6.1.12 | Continue the Lunch with a Cop program in schools. | Police | ongoing | No |  | ✓ | ✓
6.1.13 | Continue to provide an inviting social media platform for the police department to interact with the community. | Police | ongoing | No |  |  | ✓ | ✓
6.1.14 | Periodically review and work to implement the recommendations in the 2021 King County Public Safety Advisory Committee Report to improve public safety. | Police | ongoing | No |  | ✓ |  | ✓
6.1.15 | Ensure transparency by providing the annual police services report and crime data on the City’s website. Include discussion and analysis on crime trends and other public safety problems in the City. | Police | ongoing | No |  |  |  | ✓
6.1.16 | Facilitate access to the KCSO Communications Center via text message and TTY machines for hearing-impaired callers. | Police | ongoing | No |  |  |  | ✓
6.1.17 | Partner with nonprofits to distribute free locking prescription drug bags and gun cables at City Hall. | Police | ongoing | No |  |  |  | ✓
6.1.18 | Partner with NEMCo and the Fire Department for those agencies to provide educational materials on safety. | City Manager's Office | 2023 | Yes |  | ✓ |  | ✓
6.1.19 | Increase opportunities for volunteering with the police department. | Police | 2024 | No | ✓ | ✓ | ✓
Objective 6.2 Collaborate with the court, prosecutor, public defender in promoting equity and lifting people from a downward cycle in the criminal justice system.
6.2.1 | Hold regular meetings with the judges, court staff, prosecutor, and public defender to assess efforts to reduce disparities in justice services. | City Manager's Office | 2023-2028 | No |  | ✓ | ✓ | ✓
6.2.2 | Ensure electronic home monitoring is financially accessible to low-income offenders. | Court | 2023 | Yes |  | ✓ |  | ✓ | Currently not budgeted
6.2.3 | Fully participate in and contribute to the Community Court. | Court | 2023 | Yes |  | ✓ |  |  | Only funded through 2024 with one-time funding
6.2.4 | Explore drug court and other rehabilitative programs. | Court | 2026 | Yes |  | ✓
Goal 7: Housing & Human Services
Objective 7.1 Advance human services by centering marginalized communities in responding to community needs.
7.1.1 | Hire a Housing & Human Services Manager. | City Manager's Office | 2023 | No | ✓ | ✓ | ✓ | ✓
7.1.2 | Conduct a human services needs assessment and funding recommendation. | Housing & Human Services | 2023 | No | ✓ | ✓ | ✓ | ✓
7.1.3 | Conduct and implement a human services strategic plan for 2025-2030 that is centered in equity. | Housing & Human Services | 2023 | Yes | ✓ | ✓ | ✓ | ✓
7.1.4 | Oversee the ARPA-funded mental and behavioral health counseling pilot program that Center for Human Services will operate in one or more Kenmore schools. | City Manager's Office | 2023-2025 | No |  | ✓ |  | ✓ | Funded with one-time ARPA funds
7.1.5 | Use ARPA funds to pilot homelessness response and other human services programs to help people recover from the long term effects of the pandemic. | City Manager's Office | 2023-2024 | No |  | ✓ |  | ✓ | Funded with one-time ARPA funds
7.1.6 | Continue to co-lead the regional effort to site and construct an accessible 24/7 crisis center in North King County. | Housing & Human Services | ongoing | No |  | ✓ |  | ✓
7.1.7 | Build collaborative relationship with Shoreline Fire Department's Mobile Integrated Health Program. | Housing & Human Services | ongoing | No |  | ✓ |  | ✓
7.1.8 | Engage Human Services Funding Collaborative in discussions in DEIA in human services, especially with regards to human services funding application and contracting process. | Housing & Human Services | 2024 | No | ✓ | ✓ | ✓ | ✓
7.1.9 | Seek opportunities to promote human service providers and programs on city communication channels and through the creation of resource materials. | Housing & Human Services | ongoing | Yes |  |  |  | ✓
7.1.10 | Connect residents in need with state, county, and nonprofit human services agencies. | Housing & Human Services | ongoing | No |  | ✓ |  | ✓
7.1.11 | Work to educate the public to increase participation in utility cost and property tax rebates. | Housing & Human Services | 2024 | No |  | ✓ |  | ✓
Objective 7.2: Collaborate with police and justice services (court, prosecutor, public defender) in promoting equity and lifting people from the downward cycle in the criminal justice system.
7.2.1 | Consult with police and justice services to ensure human services are holistically integrated into police and justice services. | Housing & Human Services | 2024 | Maybe |  | ✓
7.2.2 | Continue to participate with and help fund the Regional Crisis Response (RCR) co-responder program. | Housing & Human Services | ongoing | Yes |  | ✓ |  | ✓ | Currently only funded through 2024 with one-time funding
7.2.3 | Partner with 211 and other agencies to provide Kenmore-specific pamphlets with human services resources for officers to distribute. | Housing & Human Services and Police | 2024 | Yes |  | ✓ |  | ✓
Objective 7.3: Promote affordable housing and support services.
7.3.1 | Prioritize, seek, and advocate for the development of mixed-used, accessible, affordable housing opportunities throughout Kenmore through partnerships with organizations including ARCH that have a commitment to DEIA values. | Housing & Human Services / | ongoing | Maybe | ✓ | ✓ | ✓ | ✓
7.3.2 | Complete the Plymouth Housing Development with 100 units of affordable housing at 30% AMI or less. | Housing & Human Services | 2022-2025 | Yes | ✓ | ✓ | ✓ | ✓
7.3.3 | Partner with health or human services providers at the Plymouth Affordable Housing development. | Housing & Human Services | 2022-2025 | Yes | ✓ | ✓ | ✓ | ✓
7.3.4 | Develop the Holt property for high density affordable housing units and a community support partner on the ground floor. | Housing & Human Services | 2024 | Yes | ✓ | ✓ | ✓ | ✓
7.3.5 | Work with ARCH to provide policies and funding for affordable housing developments in Kenmore. | Community Development & City Manager's Office | ongoing | No |  | ✓ |  | ✓
7.3.6 | Defend the 2019 Mobile Home Protection Ordinance (Ordinance #19-0481) (currently being appealed). | City Attorney | ongoing | Yes |  | ✓ |  |  | Need to budget for additional funds to litigate the appeal.
7.3.7 | Seek opportunities for outside funding for affordable housing development in Kenmore (including applying for grants and seeking partners to apply for funds through private sector funding programs). | Housing & Human Services | ongoing | Maybe |  | ✓ | ✓ |  | May need matching funds, depending on outside funding program requirements
Objective 7.4: Improve accessibility and inclusivity of city-sponsored events and services.
7.4.1 | Implement a program to accept SNAP/EBT benefits at the Farmers Market and promote financial accessibility. | Public Works Operations | 2023-2024 | Yes |  | ✓ |  | ✓ | funded only for 2023 and 2024 with one-time funding

## Needs Additional Resources
|  | Lead | Timeline | Additional Resources Needed? | D | E | I | A | Notes
Goal 1: Leadership & Operations
Objective 1.1: Foster community engagement and inclusivity in decision-making.
1.1.3 | When engaging the community in planning and decision making, make extra and affirmative efforts to bring in members of the community who have not historically participated. Provide less traditional and more inclusive and accessible opportunities for public input and engagement, such as hands-on engagement models and “pop up” engagement opportunities in neighborhoods. | City Manger's Office | 2023 | Yes | ✓ |  | ✓ |  | Will need to budget ongoing funding for this extra effort in the next biennium
Objective 1.2: Ensure equitable access and representation in city services.
1.2.1 | Identify and retain important public access and view corridors to Lake Washington and the Sammamish River for all of the public to enjoy. | Community Development | 2024 | Yes |  | ✓ |  | ✓ | Part of next Comp Plan Update
1.2.2 | Maintain and update the Parks, Recreation and Open Space (PROS) plan using the equity toolkit. Plan for more parks and amenities in underserved parts of the City and for people of all abilities. | Community Development | 2026 | Some consulting dollars will be needed |  | ✓ |  | ✓
Objective 1.3 Facilitate ways to increase diverse representation among City vendors and Committee and Commission members.
1.3.3 | Create and maintain a City of Kenmore Supplier Diversity Program for procurement; set appropriate goals for participation of minority, women, and socially and economically disadvantaged businesses. | Finance & Administration | 2025 | Yes | ✓ |  | ✓
Objective 1.5: Strengthen leadership commitment to diversity, equity, inclusion, and accessibility.
1.5.4 | Implement this 5-Year Strategic DEIA Plan and integrate it into the organization. | All Departments | 2023-2028 | Yes | ✓ | ✓ | ✓ | ✓
Objective 1.6: Ensure accountability through data collection and performance measures.
1.6.2 | Update the Strategic DEIA Action Plan every five years to align with the goals of the City of Kenmore. | City Manager's Office | 2028 | Yes | ✓ | ✓ | ✓ | ✓
1.6.5 | Conduct a City of Kenmore Community Survey every 3 years. | City Manager's Office | 2023, 2026 | Yes | ✓ | ✓ | ✓ | ✓
1.6.6 | Participate in the Human Rights Campaign Municipal Equality Index. | City Manager's Office | 2024 | TBD | ✓ | ✓ | ✓
Objective 1.7: Strengthen the Organization's Working Knowledge, Integration, and Practice of DEIA.
1.7.1 | Ensure that staff resources are allocated to the implementation of this City of Kenmore DEIA strategic initiative. | All Departments | 2023-2028 | Yes | ✓ | ✓ | ✓ | ✓
1.7.2 | Participate in mandatory, DEIA training and/or learning events every two years. (A list of training and learning opportunities shall be maintained by Human Resources). | Human Resources | 2024, 2026, 2028 | Yes | ✓ | ✓ | ✓ | ✓
Goal 2: Plans, Policies & Budgets
Objective 2.2: Engage the community in budget and policy decision-making.
2.2.2 | Use online and in person community engagement tools to gather public input. | City Manager's Office | 2023 | Yes | ✓ |  | ✓ | ✓
2.2.3 | Think outside of the box to bring more people of diverse backgrounds into policy discussions. Make extra and affirmative efforts to bring in members of the community who have not historically participated. | All Departments | 2023 | Yes | ✓ |  | ✓ | ✓ | Staffing resources needed to make the extra outreach.
Objective 2.3: Develop and advocate for affordable housing and diverse housing options.
2.3.5 | Advocate for additional affordable housing policies at federal, state, and county levels. | Community Development | underway | Yes |  | ✓
Objective 2.4: Promote economic development opportunities that benefit all Kenmore residents and businesses.
2.4.1 | Dig deeper into the experiences and outcomes of underrepresented groups in the business community and city-wide workforce. Based on what is learned, recommend policies and operational changes to lift and support these groups. | City Manager's Office | 2025 | Yes | ✓ | ✓ | ✓
2.4.2 | Increase efforts to build partnerships that support and retain local businesses and organizations, with an emphasis on supporting underrepresented and marginalized groups in the business community. | City Manager's Office | 2023/2024 | Yes | ✓ |  | ✓ |  | Will need to expand functionality of the business directory.
2.4.3 | Collect data and feedback from business community members, the Chamber of Commerce, workers, and other relevant stakeholders to best understand the needs and experiences of business owners and workers who are impacted by the policies, processes, and programs executed by the City of Kenmore. | City Manager's Office | 2025 | Yes | ✓ |  | ✓
2.4.7 | Support and promote green jobs and companies given their connection to environmental equity and social justice. | City Manager's Office | 2024 | Yes |  | ✓
Objective 2.6: Enhance recreational and cultural opportunities to improve DEIA in Kenmore.
2.6.5 | Continue to seek external funding to provide public access and recreation opportunities, especially for low income youth. | Public Works Operations | ongoing | Yes | ✓ | ✓ | ✓ | ✓
2.6.8 | Consider subsidizing swimming lessons for low income youth. | Public Works Operations | 2023-2024 | Yes |  | ✓ |  |  | Funding needs to be identified beyond 2023. Currently being funded with one-time reserves.
2.6.10 | Diversify event schedules, explore new promotion avenues, and support external community events. | Public Works Operations | ongoing | Yes | ✓ |  | ✓ | ✓ | Additional staffing resources may be needed for additonal external events
2.6.11 | Partner with nonprofits and other agencies to host community events and presentations focused on low-income populations. | City Manager's Office | 2025 | Yes |  | ✓
2.6.12 | Lead an effort to create a regional partnership to build a regional aquatic center in north King County. | Community Development | 2023-2028 | Yes |  | ✓ |  | ✓ | Feasibility study currently underway
Goal 3: Workplace
Objective 3.2: Develop and implement equitable hiring practices.
3.2.6 | Explore a work study program. | Human Resources | 2024 | Yes |  | ✓
Objective 3.4: Offer competitive employee benefits and support systems.
3.4.6 | Adopt a Commute Trip Reduction Plan that promotes non-car commute options and resources. | City Manager's Office | 2025 | Yes |  | ✓ |  | ✓
Objective 3.5: Monitor and assess workplace and workforce diversity.
3.5.1 | Research how to and begin collecting voluntary demographic data from applicants and new hires so that the City can assess whether the workplace is reflecting the greater community. | Human Resources | 2024 | Yes | ✓ |  | ✓
Goal 4: Communication & Education
Objective 4.1: Improve accessibility and inclusivity of communications across all channels.
4.1.4 | Offer translated communications in Spanish and other community languages on the website, listserv emails, and printed materials and publicize availability of translation services by phone. | City Manager's Office | ongoing | Yes |  |  | ✓ | ✓ | Spanish currently provided; need additonal resources for other languages
4.1.9 | Create a fun and engaging Civics 101 video course to help residents better understand the workings of city government. Provide Spanish subtitles. | City Manager's Office | ongoing | Yes |  |  |  | ✓ | Difficult/slow to implement with existing resources
Objective 4.2: Enhance community engagement through targeted messaging and recognition of diverse cultures and histories.
4.2.2 | Install parks interpretive signage to educate about environmental sustainability and community history. | Community Development | 2026 | Yes | ✓ |  |  |  | Completed parks projects have this signage.
4.2.6 | Invite cultural groups to host events in Kenmore, e.g., the Festival of Colors in the Spring. | Public Works Operations | 2024 | Yes | ✓ |  | ✓
Goal 5: Facility Plans & Improvements
Objective 5.1: Enhance the safety, accessibility, and inclusivity of parks and city-owned buildings.
5.1.2 | Improve access to parks and playgrounds by creating inclusive parks, including accessible components in playground structures, etc. Seek guidance from inclusive experts such as The Voice of Play. | Community Development | 2028 | Yes |  |  | ✓ | ✓
Objective 5.2: Improve transportation safety and accessibility for multiple modes of transportation so that owning an automobile isn’t the only way to get around.
5.2.1 | Develop parks and transportation plans that improve public access and mobility as well as recreational opportunities. | Community Development & Engineering Services | 2024 and 2026 | Yes |  |  |  | ✓ | 2024 for Transportation Plan and 2026 for the PROS Plan
5.2.2 | Obtain funding for and implement the first phase of the ADA transition plan, including replacing noncompliant sidewalk panels and curb ramps. Develop the next phase of the ADA transition plan to include City buildings. | Public Works Engineering | 2023-2028 | Yes |  |  | ✓ | ✓
5.2.3 | Implement and obtain funding for the adopted pedestrian facilities plan. | Public Works Engineering | 2023-2028 | Yes |  |  |  | ✓
5.2.4 | Continue to calm vehicle traffic to improve bicycle and pedestrian safety and comfort. | Public Works Engineering | 2023-2028 | Yes |  |  |  | ✓
5.2.5 | Advocate for completion of the Sound Transit Bus Rapid Transit project through Kenmore and advocate for additional bus routes and “last mile” transit options for Kenmore. | Public Works Engineering | 2023-2028 | Yes |  | ✓ |  | ✓
5.2.6 | Explore options and funding to provide more bike racks in public and private locations throughout the City. | Public Works Engineering | 2024 | Yes |  | ✓ |  | ✓
Objective 5.3: Update facility plans to reflect community needs and promote equity.
5.3.1 | Ensure capital facilities plans recognize and provide projects and programs in underserved areas. | Community Development | 2026 | Yes |  | ✓
5.3.2 | Consider community vulnerabilities related to climate and proactively respond (e.g., cooling center for impacted community members). | Environmental Services | 2024 | Yes |  | ✓
5.3.3 | Equitably provide green energy infrastructure in higher density and lower income neighborhoods. | Environmental Services | 2025 | Yes |  | ✓
5.3.4 | Reduce the heat-island effect that disproportionately affects disadvantaged neighborhoods by developing a plan to encourage and provide more trees and natural landscape to those areas. | Environmental Services | 2025 | Yes |  | ✓
5.3.5 | Equitably replace assets before reaching the end of their expected life cycle; use a fair, systematic approach to asset replacement and repair rather than the “squeaky wheel” approach. | Public Works Operations | 2025 | Yes |  | ✓
Goal 6: Public Safety & Justice Services
Objective 6.1 Advance the police department’s progress in equitably serving and responding to the community.
6.1.4 | Explore and advocate for prevention-oriented methods to reduce patrol stops that disproportionately affect people of color. For example, explore the use of technology as a replacement for traffic stops and as a way to reduce the potential for violent encounters. | Police | 2025 | Yes |  | ✓
6.1.5 | Identify low-level offenses (e.g. DWLS3) that can cause disadvantaged populations to get stuck in a vortex of economic disparity and impoverishment. Take a holistic, preventative, and healing approach to work with the prosecutor, public defender, court, and human services providers to help people out of this vortex. | Police and Justice Services | ongoing | Yes |  | ✓
6.1.9 | Participate in the King County Sheriff Department’s body worn cameras program. | Police | 2023, 2024 | Yes |  | ✓ |  |  | Body worn cameras result in added cost to the police contract.
6.1.10 | Bring back the Nurturing Trust Workshops that build trust between police and communities of color. | Police | 2025 | Yes | ✓ | ✓ | ✓
6.1.11 | Research the potential effectiveness and resources needed to produce an academy for residents to learn about police and justice services. Specifically invite people of color and marginalized groups. | Police | 2025 | Yes |  | ✓ | ✓
6.1.18 | Partner with NEMCo and the Fire Department for those agencies to provide educational materials on safety. | City Manager's Office | 2023 | Yes |  | ✓ |  | ✓
Objective 6.2 Collaborate with the court, prosecutor, public defender in promoting equity and lifting people from a downward cycle in the criminal justice system.
6.2.2 | Provide electronic home monitoring for low-income offenders. | Court | 2023 | Yes |  | ✓ |  | ✓ | Currently not budgeted
6.2.3 | Fully participate in and contribute to the Community Court. | Court | 2023 | Yes |  | ✓ |  |  | Only funded through 2024 with one-time funding
6.2.4 | Explore drug court and other rehabilitative programs. | Court | 2026 | Yes |  | ✓
Goal 7: Housing & Human Services
Objective 7.1 Advance human services by centering marginalized communities in responding to community needs.
7.1.3 | Conduct and implement a human services strategic plan for 2025-2030 that is centered in equity. | Housing & Human Services | 2023 | Yes | ✓ | ✓ | ✓ | ✓
7.1.9 | Seek opportunities to promote human service providers and programs on city communication channels and through the creation of resource materials. | Housing & Human Services | ongoing | Yes |  |  |  | ✓
Objective 7.2: Collaborate with police and justice services (court, prosecutor, public defender) in promoting equity and lifting people from the downward cycle in the criminal justice system.
7.2.1 | Consult with police and justice services to ensure human services are holistically integrated into police and justice services. | Housing & Human Services | 2024 | Maybe |  | ✓
7.2.2 | Continue to participate with and help fund the Regional Crisis Response (RCR) co-responder program. | Housing & Human Services | ongoing | Yes |  | ✓ |  | ✓ | Currently only funded through 2024 with one-time funding
7.2.3 | Partner with 211 and other agencies to provide Kenmore-specific pamphlets with human services resources for officers to distribute. | Housing & Human Services and Police | 2024 | Yes |  | ✓ |  | ✓
Objective 7.3: Promote affordable housing and support services.
7.3.1 | Prioritize, seek, and advocate for the development of mixed-used, accessible, affordable housing opportunities throughout Kenmore through partnerships with organizations including ARCH that have a commitment to DEIA values. | Housing & Human Services / | ongoing | Maybe | ✓ | ✓ | ✓ | ✓
7.3.2 | Complete the Plymouth Housing Development with 100 units of affordable housing at 30% AMI or less. | Housing & Human Services | 2022-2025 | Yes | ✓ | ✓ | ✓ | ✓
7.3.3 | Partner with Bastyr University for a community health clinic at the Plymouth Affordable Housing development. | Housing & Human Services | 2022-2025 | Yes | ✓ | ✓ | ✓ | ✓
7.3.4 | Develop the Holt property for high density affordable housing units and a community support partner on the ground floor. | Housing & Human Services | 2024 | Yes | ✓ | ✓ | ✓ | ✓
7.3.6 | Defend the 2019 Mobile Home Protection Ordinance (Ordinance #19-0481) (currently being appealed). | City Attorney | ongoing | Yes |  | ✓ |  |  | Need to budget for additional funds to litigate the appeal.
7.3.7 | Seek opportunities for outside funding for affordable housing development in Kenmore (including applying for grants and seeking partners to apply for funds through private sector funding programs). | Housing & Human Services | ongoing | Maybe |  | ✓ | ✓ |  | May need matching funds, depending on outside funding program requirements
Objective 7.4: Improve accessibility and inclusivity of city-sponsored events and services.
7.4.1 | Implement a program to accept SNAP/EBT benefits at the Farmers Market and promote financial accessibility. | Public Works Operations | 2023-2024 | Yes |  | ✓ |  | ✓ | funded only for 2023 and 2024 with one-time funding